## Slide 1: Face to Face Outreach with Texas Tech University Health Sciences Center El Paso
Sarah Martin
Adrianne Harrel

## Slide 2
West Texas
Along the Border
A Cultural Education:
The people
The lifestyle
The land

## Slide 3: The Beginning
Doctors, counselors and medical school staff
No experience with outreach
Why didn’t everyone didn’t want to join our awesome (and free) projects?
Pandemic issues
Phone calls: front desk staff trained to keep out the riffraff
Too many emails
Not enough progress

## Slide 4: Planning Retreat
Face to Face Outreach Strategy
  Dates for overnight travel (monthly 2 or 3 consecutive days)
  Dates for local travel (biweekly EP County)
  TCHATT - Identify ISDs in area not enrolled
  CPAN - Identify Clinics in areas not enrolled
  Plan travel routes to visit areas with identified and not enrolled for both CPAN & TCHATT

## Slide 5: Plan a Road Trip
Identify Area
Identify route that works within the time frame
Try to make appointments
Don’t worry too much if you only few
Assign each person a role
  Adrianne Harrel- interviews all the locals
  Sarah- makes sure people know she’s a doctor and so they should definitely talk to her
  Bethany- makes sure we behave ourselves

## Slide 6
TCHATT Folder
CPAN Folder

## Slide 7
Valentine (TCHATT) Day 1
Marfa (TCHATT/CPAN) Day 1
Presidio (TCHATT/CPAN) Day 1
Terlingua (TCHATT/CPAN) Day 2
San Vicente ISD (TCHATT) Day 2
Marathon (TCHATT) Day 2
Sanderson (TCHATT/CPAN) Day 2
Del Rio (CPAN) Day 2/3
Eagle Pass (TCHATT/CPAN) Day 3
Ozona (TCHATT/CPAN) Day 4
Sheffield (TCHATT/CPAN) Day 4
Iraan (TCHATT/CPAN) Day 4
Fort Stockton (TCHATT/CPAN) Day 4
Trip #1 (4 Days)
Fort Stockton (TCHATT) Day 1
Grandfalls (TCHATT) Day 1
Marathon (TCHATT) Day 2
Sanderson (TCHATT) Day 2
Ozona (TCHATT/CPAN) Day 2/3
Del Rio (TCHATT/CPAN) Day 3
Brackettville (TCHATT) Day 4
Trip #3 (4 Days)
Marfa (TCHATT/CPAN) Day 1
Alpine (TCHATT/CPAN) Day 1
Fort Davis (TCHATT/CPAN) Day 1
Balmorhea (TCHATT) Day 1
Monahans (TCHATT/CPAN) Day 2
Kermit (TCHATT/CPAN) Day 2
Wink (TCHATT) Day 2
Pecos (CPAN) Day 2
Trip #2 (2 Days)

## Slide 8: Follow Up Phase
TCHATT
Schedule initial trainings for interested ISDs
Schedule follow up meetings for those not as interested
CPAN
Add to Trayt
Add to CME and Project ECHO Listservs

## Slide 9
38 Districts in Region:
15 Active MOUs
12 NEW MOUs in process/contracting
9 NEW Districts in talks with us
1 Services by CAP Fellow /Free Clinic
1 ISD tabled at this time
Enrolled 18 NEW CPAN Clinics
Enrolled 50 NEW Providers
Increased CPAN Consults
  August 2021 – 18 Consults
  August 2022 – 35 Consults
TCHATT
CPAN