## Slide 1: Q1 Metrics for ARPA-Funded Initiatives
TCMHCC Executive Committee Meeting
February 6, 2023

## Slide 2
ARPA Overview
Funding Start Date: September 1st, 2022
Phase: Launch
  Administration
    Contracts
    Funding
  People Operations
    Hiring
    Training
    Onboarding
  Project Operations
    Program Recruitment & Outreach
    Program Modifications
    Tech Design and Implementation
Next Steps:
  Detailed quarterly Power BI reports to be distributed to individual HRIs and HRI EC members
  Follow-up meetings to discuss project trajectory and action steps (if needed)
ARPA CPAN Projects
ARPA TCHATT Projects
ARPA CPWE/CAP/Workforce Projects
Risks and Actions

## Slide 3: ARPA-Funded CPAN Projects
 | Direct Consults | BCM, TTUHSC, TTUHSC EP, UT Dell MS, UTHSCH, UTHSCSA, UTHSCT, UTMB
 | DM/Text Add-On | BCM, UT Dell MS, UTHSCH, UTHSCT, UTSW
 | Pediatric CoCM | MMHPI, BCM, Dell, TTUHSC, TTUHSC EP, UNTHSC, UTHSCSA, UTRGV, UTSW
 | PeriPAN | BCM, TTUHSC, UT Dell MS, UTSW
 | SAFETY-A | BCM, TAMUHSC, TTUHSC, UT Dell MS, UTHSCH, UTMB, UTSW
89
Direct Consults
8
PCP Education/ Training Sessions
515
New Providers Enrolled
42k
Children Initially Reached by CoCM
121
Consults Initiated via Text/DM
70
Consultations Provided

## Slide 4: ARPA-Funded TCHATT Projects
 | Additional Sessions | TAMUHSC, TTUHSC, TTUHSC EP, UT Dell MS, UTHSCH, UTMB, UTRGV
 | Anxiety Services | BCM, TTUHSC, UTHSCH, UTHSCSA
 | A-SUD | TTUHSC, UT Dell MS, UTHSCH, UTHSCSA
 | Bilingual Trauma | TTUHSC, UTHSCSA
 | More TCHATT Regions | TTUHSC, UTHSCH, UTHSCSA, UTMB, UTRGV
 | Evidence-Based Groups | TTUHSC
 | Trauma-Focused Expansion | TAMUHSC, TTUHSC, UT Dell MS, UTHSCH, UTHSCSA, UTMB
 | YAM/YAM Hub | TAMUHSC, TTUHSC, UT Dell MS, UTHSCH, UTHSCSA, UTHSCT, UTMB, UTSW
1963
Student Sessions
933
Unique Youth Served
266k
Additional Lives Covered
4578
Youth Receiving MH Education/Training
52
Group Sessions
53
Providers Trained

## Slide 5: ARPA-Funded CAP/CPWE/Workforce Projects
 | CAP Fellowships and Support | UT Dell MS, UTSW, TTUHSC EP
 | LMHAs | TTUHSC, UT Dell MS, UTHSCH, UTSW
 | Workforce Expansion/Training | BCM, TAMUHSC, TTUHSC, TTUHSC EP, UT Dell MS, UTHSCH, UTHSCSA, UTSW
0
CAP Appointments Supervised
107
Months of Training Provided
2289
Appointments/
Sessions Provided
0
Resident/Fellow Clinic Hours
0
Additional Community Centers Partnered
0
Residents Trained in CHCs
0
Hours Supervision/ Training by CAP Sup.

## Slide 6: ARPA Project Risks and Actions
Pending Contracts/MOUs
Pending contacts and MOUS causing delays in funding and program operations
  UTS will follow-up on outstanding contracts
Outreach
Cold-calling outreach strategy not producing expected enrollment results
  HRI will focus on direct visits, mailers, and other strategies to increase enrolled providers/trainees
Difficulties outreaching to Residents/Fellows due to clinic rotations
  HRI will deliver enrollment presentation during trainee didactics
Low PCP interest in direct consultations pilot
  HRI will focus on alternative outreach strategies to increase CPAN call volume, and access to direct consults
  HRI has expanded pilot catchment area to reach more providers
Tech
Staff are unable to indicate when a direct consultation was completed in TRAYT
  COSH consulted for request/update of this feature in TRAYT
  HRI will utilize an internal tracker pending feature updates from TRAYT
Lantana 8x8 system requires HIPAA compliance for the text/DM feature
  HRI will distribute communications materials to providers on how to submit HIPAA compliant texts for DM/Text project
Requested TRAYT modifications are pending
  HRI will manually track the number of youth/sessions in their EHR pending TRAYT updates
  Requested assessments are in queue in TRAYT development roadmap
IT/Phone/Tech issues at LMHA have impacted the ability to provide client care
  IT issues are being resolved through IT

## Slide 7: ARPA Project Risks and Actions
Privacy
A-SUD is a service covered by Code of Federal Regulations title 42 part 2, and requires additional privacy protections
  HRI is working with EHR to develop A-SUD compliance notes, and will follow additional internal protocols to increase security
  HRI is collaborating with Legal and Compliance on designing A-SUD operational procedures
  UTS is working with legal, COSH, and TRAYT on internal privacy controls
Clinic is managing referral compliance surrounding documentation and 42CFR
  42CFR being reviewed by HRI Compliance Officer
Staffing
Difficulties recruiting and hiring staff (no applicants, lacking qualifications, rejecting due to salary, market competition)
  Some HRIs have restructured internally to allocate savings to other positions
  HRIs are reprioritizing needed hires
  HRIs are working with HR to increase visibility of positions
  Some HRI managers are taking clinical caseloads pending clinical hires
  UTS is keeping track of open positions and hires based on monthly status report from HRIs
  UTS is posting positions on UTS job board
  HRIs are training more facilitators to expand reach of programming where possible
  HRI Budgets have been adjusted increase pay range for clinical professionals
Staff turnover impacting operations
  HRI Executive Leadership is completing an internal review
HRI having trouble identifying sites for LMHA expansion
  HRI will explore options for incoming staff to allocate time to this project
Limited CAPS recruited to complete sessions
  HRIS to continue recruitment, onboarding, and training
  Staff has now been established to support CAPs
Referrals
Incomplete referrals being submitted by community
  HRI is looking into community referrals/structure and exploring strategies in TCHATT Leadership meeting
Difficulty contacting referred patients/limited parental involvement
  Explore strategies to increase involvement of support systems in TCHATT Leadership Meeting
  HRIs will utilize multiple methods of outreach including collaboration with referral providers to increase enrollment
Low referral rates in large districts
  HRIS are collaborating with their district partner to increase referrals

## Slide 8
Questions?