## Slide 1
Texas Child Mental Health Care Consortium
Melanie Susswein, MSW

## Slide 2
Agenda
CHC Overview
Project Overview
CPAN
Q&A
1
2
4
3

## Slide 3
OUR team
Mike Mackert
Director
Nicole Kirschten
Graphic Designer
Jessica
Hughes Wagner
Deputy Director
Patricia Semenov
Center Administrator
Eddie Silva
Web Developer
Melanie Susswein
Program Manager
Nick Brothers
Copywriter

## Slide 5
Notes: CHC Message Design Process

## Slide 6: TCMHCC Project Aims
CPAN
Increase number of newly enrolled PCPs.
Increase utilization of CPAN services by enrolled PCPs.
TCHATT
Increase utilization of TCHATT services by currently enrolled schools.
*Specific measurable goals and targets developed in collaboration with UTS and COSH for the communication evaluation plan.​

## Slide 7
Project onboarding
Information gathering
Formative research
Initiating creative development
FALL 2021
Formative research
Develop and refine outreach and communication plan
Collaborate with physician engagement expert
Provide HRIs with initial tools and strategies
Fall +
Winter 2021
Direct mail distribution
Digital ads in market
Paid search/keyword marketing
Paid partnerships
Overview video launch
Spring +
Summer 2022
Continued engagement and implementation of communication plan
Evaluation plan
Fall +
Winter 2022
timeline

## Slide 8
STRATEGY + TACTICS
Direct Mail | Paid Partnerships | Digital Ads | Email
Website | Events | Video | SEO + Marketing
Tactics and strategies emerging from our research:

## Slide 9: Thus Far- focus on CPAN

## Slide 10: Activities Thus Far
Background
Environmental scan of CPAN ecosystem
Meetings
Physician consultant
COSH touch point
Project meetings
Data management
HRI Individual Meetings with COSH
CME
ECHO
Engagement Strategy Review
Review of website and social media platforms​

## Slide 11: Activities Thus Far
Creative
Review of existing materials and brand guides
Developed initial social media themes
Formative Research
Interviews with each HRI
Interview with Physician outreach consultant
Interviews with providers (in progress)
Interviews with national CPAN experts (in progress)

## Slide 12: Social media templates – draft
CME
CPAN Fact
Did you know?
In the Media
Endorsement

## Slide 14: Q & A