## Slide 1
Texas Child Mental Health Care Consortium
December 2025
Melanie Susswein, MSW

## Slide 2
Agenda
Our Scope: Project Year 5
A Closer Look: Consortium Website Rebuild
Upcoming Steps & Priorities
1
2
3

## Slide 3
CHC Outreach and communication scope
Project year 5
Reenvision and rebuild the Consortium public-facing website to make it more intuitive, usable, current, complete, & easy to navigate.
Focused on reorganizing current written content and making information consistent across programs & initiatives as well as audience specific.
New overall look and feel while maintaining key components.
Creation of best practices guidance for clinician trainers and experts.
Revision and standardization of CPAN, PeriPAN, and TCHATT presentation slides to align with best practices.
Nurture 11 ongoing stakeholder relationships while forging strategic new relationships, including to engage rural hospitals.
Updated outreach plan, ongoing consultations, and Summit presentations.
Social media video and dynamic content strategy.
Materials development and updates to support priorities.
Website rebuild
Outreach & engagement
Presentation standardization

## Slide 4
TCMHCC website rebuild project
Methodology & progress September–November (Q1)
Ongoing with foundational inquiries complete.
Audit of current website content & architecture. Review of over 50 websites with a similar focus or audience, or displaying visual best practices, for design and content concepts. Analysis of core web best practices and our audiences.
16 interviews with TCMHCC leaders and key stakeholders who oversee and support Consortium initiatives. Analysis of findings & direct content implications.
Creation of site map & initial architecture with direct stakeholder input, plus early design concepts.
Content strategy and inventory underway, moving into finer levels of detail.
Discovery & planning phase

## Slide 5
Home
How to Access Services
School Resources
Schools
Clinicians
How to Access Services
Pediatric Clinicians
Perinatal Clinicians
School Counselors, Clinicians, & Educators
Clinical Resources
Families
Find Help & Resources
Initiatives & Programs
Psychiatry Access Programs for Clinicians
(CPAN, PeriPAN)
School Mental Health (TCHATT, YAM)
Research Initiatives
(YDSRN, CTRN, NECMHR)
Workforce Development
(CPWE, CAP, OWE)
Free CME Training
Free CME Calendar
Project ECHO
Recorded CME Training
Request a Training
Impact & Publications
Reports
Research Publications
Resources
Clinical Resources
> Mental Health Screening
> Medication Guides
> Diagnosis-Specific Resources
> Toolkits
> Case of the Month
> Clinical Pearls
> Research Publications
School Resources
Family Resources
About Us
Need, Mission, & Vision
How to Access Services
Meet the Team
Executive Committee
Reports
Careers
Contact Us
Dashboard and Metrics
Psychiatric Clinicians
> Free CME Training
Repeating categories / doors to content:
Clinical Resources (2x)
Programs (2x) – enter by audience or program name/domain
School Resources (2x)
Family Resources (2x)
Research Publications (3x, including through Research Initiatives)
Reports (2x)
CME Training (3x)
How to Access Services (3x)
Plus, cross-linking to internal pages within written content on individual pages, as relevant.
Current site map & information architecture
In development

## Slide 6
TCMHCC website rebuild project
Content strategy and inventory will continue, with the start of the Writing, Designing, and Prototyping Phase now and into December and into early 2026.
Finer strategy and content discussions.
Visual design and content development, including mockups, writing, and reviews will continue throughout 2026.
Next steps

## Slide 7
Thank you.
Questions?